## BID EVALUATION
KEYWORDS | DESCRIPTION | Notes
Solicitation / RFP / RFQ / RFI | Soliciation Document+Drawings
Bid instructions & deadlines | Scope of work
Substitutions/Equivalents | Confirm the project allows substitutes or equivalent fixtures. Substitution Permitted – Qualified or Approved Equivalent Accepted | Substitution Approval Process - If substitutions are allowed but require prior approval, the approval date must be 10 days before bid submission. The approval request must also be at least 1–2 days ahead of the current date, to ensure we have preparation time.
Experience & references | State-wise and category-wise project status
Labor requirements | Check for these keywords - prevailing wages and davis bacon
Site investigation | Pre-Bid Meeting Requirements (Mandatory or Not) | Distributor List (BoB)
subcontractors/Vendors | Local Vendor Eligibility Clause – Refer to Bid Documentation
Buy American / BABA compliance | (MADE IN US) & Funded by DOE (Department of energy) | FAR No. - ?
Bonds | Bid Bond and Performance Bond Deadline Alerts (High Priority)
Lead Time Consideration | Feasibility check required for local sourcing. | If most items are sourced locally via websites due to short lead times and US vendors lack availability, bidding may not be cost-effective.

## CHECKLIST
Turn Key Project Checklist
Proposal Development
Customer Submission
Questionnaire Completion
Award Status (Won/Lost)
Site Visit
Subcontractor Identification (Trigger Point)
Project Manager Assignment (Overall Responsibility)
Material Lead Time Assessment
Product Staging
Installation Start
Commissioning (Final Check)
Site Visit (Post-Installation)
Handover with Closure Documentation
Supply only
Proposal Preparation- Handled by Business Development
Supply :- Operations -> Triggered by operational requirements -> Ends with completion of the supply process

## STATE LICENSES
States | License Details
States | Availablity | License Details | IKIO / Subs | Subs Details Priority 1 | Subs Details Priority 2 | Subs Details Priority 3
Alabama | Yes |  | Subs | Gadsden Electric | - | -
Alaska | No | - | - | - | - | -
Arizona | Yes | ROC183751 | Subs | Allstate Utility Construction, LLC | LED Solutions | Negawatt Partners, LLC
Arkansas | Yes |  | Subs | Negawatt Partners, LLC
California | Yes |  | Subs | LED Solutions
Colorado | yes |  | Subs | 5280 Electrical
Connecticut | yes | #ELC.0208548-E1 | Subs | ETS Electrical Construction
Delaware | No
Florida | yes |  | Subs | Optiva lighting & Electrical services, LLC
Georgia | yes |  | Subs | Optiva lighting & Electrical services, LLC
Hawaii | No
Idaho | No
Illinois | yes |  | Subs | greenlight national
Indiana | yes |  | Subs | LED Indy | Midstate Energy
Iowa | yes |  | Subs | Volt Tech Electric
Kansas | No
Kentucky |  |  |  | Check with Greg
Louisiana | Yes | 75356 | Subs | Electric Lighting LLC
Maine | Yes |  | Subs | Wight Electric
Maryland | No
Massachusetts | No
Michigan | yes | 6105850 | Subs | Thunder Bay Electric Inc.
Minnesota | yes |  | Subs | First Nation Electric | Lyon's Electric LLC
Mississippi |  |  |  | inder will confirm
Missouri | No
Montana | No
Nebraska | Yes | 49170 | Subs | Stoller Electric Service
Nevada |  |  |  | need to check with jeremy
New Hampshire | Yes |  | Subs | Wight Electric
New Jersey | No
New Mexico | No
New York | yes |  | Subs | INF
North Carolina | yes |  | Subs | Optiva lighting & Electrical services, LLC
North Dakota |  |  |  | Inder will provide
Ohio | yes |  | Subs | Firelands Electric, Inc.
Oklahoma | yes |  | Subs | Negawatt Partners, LLC
Oregon | yes |  | Subs | 5280 Electrical
Pennsylvania | yes | 60678 | Subs | City Light Electric
Rhode Island | yes |  | Subs | Premier electrical services
South Carolina | No
South Dakota | yes |  | Subs | Muth Electric Inc.
Tennessee | yes |  | Subs | Optiva lighting & Electrical services, LLC
Texas | yes |  | Subs | Negawatt Partners, LLC | METCO Engineering Inc.
Utah | yes |  | Subs | 5280 Electrical
Vermont | No
Virginia | yes | 2705189492 | Subs | K&M Electrical LLC
Washington | yes |  | Subs | Reeves Company
West Virginia | yes | WV062018 | Subs | Flash Electrical and Plumbing
Wisconsin | yes |  | Subs | greenlight national
Wyoming | No